## Slide 1
OUIBOO
MVP launch readiness and production-hardening story
A concise project presentation for the travel marketplace platform: product shape, architecture, hardening completed, verified demo path, and remaining public-production blockers.
82%
controlled MVP demo readiness
74%
public production readiness
0
high audit vulnerabilities
June 10, 2026
Sources: repository docs and hardening execution report
01

## Slide 2
PRODUCT SYSTEM
Ouiboo organizes travel demand, agency supply, and platform governance into one marketplace loop.
The platform is not a single storefront; it is three role-specific applications coordinated by one API, one data model, and financial controls.
Traveler
Search trips
Book sessions
Pay securely
Review + wishlist
Agency
Create supply
Manage bookings
Message travelers
Withdraw earnings
Admin
Approve agencies
Monitor finance
Resolve refunds
Govern quality
Shared capabilities: Auth/RBAC • Trips • Bookings • Payments • Wallet • Reviews • Messaging • Notifications • Analytics
Sources: repository docs and hardening execution report
02

## Slide 3
HARDENING PASS
The second pass attacked deployment blockers first: money precision, distributed safety, and security controls.
The changes are operationally focused: reduce financial correctness risk, make API replicas safe, and make launch readiness auditable.
Money precision
Prisma money fields converted to Decimal; API money contract becomes decimal strings; provider minor units use Decimal arithmetic.
Fixed
Distributed runtime
Redis-backed rate limiting, Redis health checks, BullMQ worker entrypoint, API-local cron removed.
Fixed
Security/RBAC
Analytics guard gaps fixed; route inventory created; remaining endpoint-by-endpoint authorization failures need full E2E coverage.
Partial
Deployment
Prod compose example, Docker CMD fix, runbook, managed Postgres/Redis/storage assumption documented.
Partial
E2E evidence
Unit/app builds pass; full API E2E timed out locally and remains launch verification.
Open
Sources: repository docs and hardening execution report
03

## Slide 4
RUNTIME ARCHITECTURE
The target runtime separates user traffic from scheduled work and shared state.
API replicas now rely on Redis for rate limit state, while scheduled maintenance belongs to a worker queue rather than per-replica cron.
Traveler
Agency
Admin
NestJS API
/api/v1
Postgres
Prisma
Redis
rate limit + queue
BullMQ Worker
reminders + FX + cancels
Production implication: horizontal API scaling becomes safer only when Redis, worker idempotency, migration discipline, and readiness checks are exercised together.
Sources: repository docs and hardening execution report
04

## Slide 5
SECURITY CONTROLS
Security is now documented as an endpoint inventory, but launch needs failing-authorization proof.
The right question is no longer whether RBAC exists; it is whether every route proves auth, role, ownership, pagination, sorting, filtering, and rate limits.
Auth guard
JWT boundary on private APIs
verify all routes
Role guard
traveler / agency / admin
analytics fixed
Ownership
tenant + resource owner checks
needs E2E failures
Pagination
bounded list endpoints
remaining rollout
Input rules
sort allowlists + filters
needs audit closure
Rate limits
Redis counters by route/user/IP
production REDIS_URL
Sources: repository docs and hardening execution report
05

## Slide 6
DEMO READINESS
The controlled demo is seeded and build-verified; full API-backed E2E remains the public-launch gate.
This is the practical readiness view for a stakeholder demo versus a real external production launch.
API build + unit tests
passed
Traveler / Agency / Admin builds
passed
Dependency audit high
0 findings
Seeded demo data
available
Root build
timed out locally
API E2E
not fully verified
Recommendation: use the current state for a controlled MVP demo, but do not open public production until E2E and deployment rehearsal pass cleanly.
Sources: repository docs and hardening execution report
06

## Slide 7
LAUNCH PATH
The remaining production work is a short, concrete launch rehearsal rather than an open-ended rebuild.
The sequence must prove the system under production-like conditions: backup, migration, deploy, observe, rollback.
1
Freeze
lock env + release candidate
2
Back up
snapshot Postgres + storage
3
Migrate
Prisma migrate deploy
4
Deploy
API, worker, three frontends
5
Observe
logs, health, Redis, DB
6
Rollback
exercise documented rollback
Blocking proof: a clean run through this sequence on staging with monitoring and rollback evidence attached to the release notes.
Sources: repository docs and hardening execution report
07

## Slide 8
DECISION
Proceed with a controlled MVP demo; hold public production until four blockers are closed.
The platform is materially stronger after hardening, but production confidence must be earned through real flows and operational rehearsal.
Demo now
Seeded accounts, builds passing, audit clean, core flows ready for guided validation.
Do not public-launch yet
Full API E2E, upload safety, endpoint pagination/RBAC proof, and staging rehearsal are still open.
Launch blockers
API-backed E2E passes
Payment webhook replay tests
File upload malware/content scanning
Production migration + rollback rehearsal
Updated readiness: controlled demo 82% / public production 74%
Sources: repository docs and hardening execution report
08